Project status report M1
Delivery 2012 Wk 49

# Dependency Analysis for Kactus2

Reporting period:	2012 December (Wk 49 – Wk 52)

Project group:	Joni-Matti Määttä	joni-matti.maatta@tut.fi
Mikko Honkonen	mikko.honkonen@tut.fi
Tommi Korhonen	tommi.korhonen@tut.fi

Delivery: Joni-Matti Määttä, Mikko Honkonen, Tommi Korhonen, Timo D. Hämäläinen, Marko Hännikäinen, Francescantonio Della Rosa

## 1. Description of work
The meetings with the client continued while functional specification was being written. The team finished the first complete version of the functional specification and began work on the technical specification.

1.1. Results achieved
Functional specification

1.2. Problems encountered
-

1.3. Changes to the project plan
Budget redone from scratch to better illustrate how the costs would be in a real scenario.

1.4. Immediate actions needed
The first milestone meeting should be organized as soon as possible.

## 2. Status of Tasks (finishing wk 52, the last week of this reporting period)
## 3. Status of Deliverables (finishing wk 52, the last week of this reporting period)

## 4. Usage Statistics (finishing wk 52, the last week of this reporting period)

4.1. Working hours of the group
* Planned for complete project: 619 h person hours total

4.2. Working hours per group member

4.3. Working hours per task

## 5. Summary vs. whole project

	Planned	Realized	%
Project results achieved / (not number of deliverables or similar simple metric)	Qualitative, subjective / self-assessment		10%
Calendar weeks / (on the timeline from beginning wk to end wk)	24 wk	8 wk	33%
Person hours	619 h	61,20 h	10%
Budget	15 986 €	680 €	4%

Task Table in the Project plan:

Deliverables Table in the Project plan:

ID	Deliverable Name	Type	Delivery Week	Recipients
D1	Functional specification	Document	2012 Wk 50	Client, assistant
D2	Technical specification	Document	2013 Wk 2	Client, assistant
C1	Qt implementation of the tool	Codes	2013 Wk 15	Client
FR	Final report	Document	2013 Wk 16	Client, assistant
M1 / M2	Monthly status reports 2012 (Nov, Dec)	Document	2012 Wk 49 / 2013 Wk 2	Assistant
M3 / M4 / M5	Monthly status reports 2013 (Jan, Feb, Mar)		2013 Wk 6 / 2013 Wk 10 / 2013 Wk 14	Assistant
P1	Project plan presentation	Presentation	2012 Wk 48	Seminar
P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 16	Seminar

Schedule Chart in the Project plan: