Final Report
Dependency Analysis Tool
for Kactus2
Version 1.0

TUT	Department of Pervasive Computing	TKT-2527 Project Work
Author: Joni-Matti Määttä
Joni-Matti Määttä, joni-matti.maatta@tut.fi
Mikko Honkonen, mikko.honkonen@tut.fi
Tommi Korhonen, tommi.korhonen@tut.fi

Document State: Final		Modified: 2013-05-14

Version History

Version	Date	Author(s)	Summary of Changes
0.1	2013-04-10	T. Korhonen	Used document ”Project Plan.odt” as a template and modified it to Final Report.
0.2	2013-04-24	T. Korhonen	Added content to chapters 1 and 4.
0.3	2013-04-30	J.-M. Määttä	Added content to chapters 3, 4 and 5.
0.4	2013-05-07	M. Honkonen	Added content to chapters 4, 5 and 6.
0.5	2013-05-08	T. Korhonen	Added content to chapter 4 (Budget)
0.6	2013-05-10	T. Korhonen	Added content to chapters 4 and 7.
0.7	2013-05-12	M. Honkonen	Improved various parts.
0.8	2013-05-12	J.-M. Määttä	Added the realized time table and added claficiations here and there.
1.0	2013-05-14	J.-M. Määttä	Finalized the document.

Acceptance signatures

________________________________
Joni-Matti Määttä
Project Manager

________________________________
Timo D. Hämäläinen
Client

Expected credit units: 7 cp
Executive summary

Kactus2 is an open-source IP-XACT-based EDA tool developed at Tampere University of Technology. It aims for easier product management and development than any other tool on the market, including commercial ones. Dependency management is an essential requirement for any tool which deals with HW projects consisting even of thousands of source files. Managing such projects becomes extremely hard if the tool does not offer any help for managing dependencies between the source files. This is important especially when source modifications are made to be able to keep the whole project in compilable form at all times.
The purpose of the project was to develop a dependency analysis tool that integrates with Kactus2 and offers various advantages compared to other EDA tools. The project group consisted of three persons with varying backgrounds in software development. The project took six months to finish. The dependency analysis tool was successfully integrated into Kactus2.

Table of Contents

# Introduction

## Overview
Dependency analysis tool for Kactus2 project is made for Tampere University of Technology as a project work for course TKT-2527. The purpose of the project is to develop a dependency analysis tool to manage dependencies between various different files in a hardware project. The tool is to be integrated with Kactus2 which is being developed at the Department of Pervasive Computing at Tampere University of Technology. The project group consists of three persons with varying backgrounds in software development. The project is estimated to take five months.
## Target and Scope of the Document
This document is the final report for the dependency analysis tool for Kactus2 project. Document summarizes information from the entire time span of the project, such as what the actual project schedule was in comparison to the planned, and whether or not the project reached the goals set in the project plan.
The document provides the course staff information about how the project was implemented.
## Structure of the Document
This document is divided into 10 chapters. Chapter 1 gives an introduction to this document as a whole. Chapter 2 illustrates the project organization, including information about the project team, the client and other interest groups. Chapter 3 summarizes the planned project. In chapter 4, realized implementation of the project is explained. In chapter 5, conclusions are drawn between planned and realized project. Chapter 6 discusses results of the project. Chapter 7 talks about expected credit units. Chapter 8 is preserved for comments and opinions on the course. Finally, Chapter 9 lists all used references, and Chapter 10 is for listing appendices.
# Project Organization

## Project Members
The project consisted of three members:
Joni-Matti Määttä
joni-matti.maatta@tut.fi
Joni-Matti was the project manager and SW architect in the project.
Mikko Honkonen
mikko.honkonen@tut.fi
Mikko was the test lead in the project. He was also responsible of major development tasks in the project.
Tommi Korhonen
tommi.korhonen@tut.fi
Tommi was the UI specialist in the project. He also did software development in the project.
All members in the project group took part in writing the documentation for the project. Joni-Matti was in charge of the project plan and technical specification document. Tommi was in charge of the functional specification document. Mikko was in charge of the testing plan.
## Client
Timo D. Hämäläinen (timo.d.hamalainen@tut.fi) was the client of the project.
## Other Interest Groups
Other interest groups included the TKT-2527 Project Work course staff, Kactus2 development team and end users. Monthly reports were done for the course staff about the progress of the project. All project documents were also sent to the course staff. The original Kactus2 development team was informed about any large decisions made in the project so that integrating the final product into Kactus2 was as effortless as possible.

# Summary of the planned project
## Project Background
Large-scale embedded HW projects require thousands of files, which becomes a nightmare to manage without proper tools. The most challenging aspect with a large amount of files is managing dependencies between files to prevent accidentally breaking the source by modifications.
Kactus2 is an open-source IP-XACT-based EDA tool which aims for easier product management and development. It is developed in TUT, in the Department of Prevasive Computing. Dependency management is an essential requirement for having an improved workflow in Kactus2.
The purpose of the project was to create a dependency analysis tool for Kactus2 in order to resolve dependencies between various source files related to a hardware project. It was required that the tool could parse dependencies in C/C++ and VHDL and display them in a so-called table-graph view.
## Project Objectives
### The Objectives of Different Interest Groups
The objectives of the project group were:
- To finish a whole software development project in schedule (required)
- To have a working product integrated into Kactus2 (requested)
- Learn about project management and scheduling (requested)
The objectives of the client were:
- The dependency analysis tool should have at least as good usability as Kactus2 itself (requested)
- The tool should improve the user experience and offer features that truly make the use easier (requested)
- The tool should be well integrated into Kactus2 so that it does not look like a part of its own (required)
### Technical Objectives
The technical objective of the project was to develop good, modular software component that is easy to integrate into any Qt-based application (requested).
## Deliverables
Table 3.1 summarizes all project deliverables.
Table 3.1: Project deliverables.
ID	Deliverable Name	Type	Delivery Week	Recipients
D1	Functional specification	Document	2012 Wk 50	Client, assistant
D2	Technical specification	Document	2013 Wk 2	Client, assistant
C1	Qt implementation of the tool	Codes	2013 Wk 15	Client
FR	Final report	Document	2013 Wk 16	Client, assistant
M1 / M2	Monthly status reports 2012 (Nov, Dec)	Document	2012 Wk 49 / 2013 Wk 2	Assistant
M3 / M4 / M5	Monthly status reports 2013 (Jan, Feb, Mar)		2013 Wk 6 / 2013 Wk 10 / 2013 Wk 14	Assistant
P1	Project plan presentation	Presentation	2012 Wk 48	Seminar
P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 16	Seminar

### Reports and Documentation
#### Technical Document 1 (D1): Functional Specification
The functional specification describes the behavior of the system from the user perspective. It specifies how the system reacts to given input, providing the team the information necessary to write the technical specification. The client is required to accept the functional specification.
The functional specification document was delivered to the client and the course staff via email, at the date specified in Table 3.1.
#### Technical Document 2 (D2): Technical Specification
The technical specification describes the system architecture. It is written in such way that the entire system can then be implemented based only on information found in it. The technical specification is required before the system can be implemented.
The functional specification document was delivered to the client via email, at the date specified in Table 3.1.
#### Final Report (FR)
The final report summarizes information from the entire time span of the project, such as what the actual project schedule was in comparison to the planned, and whether or not the project reached the goals set in the project plan.
The final report will be delivered to the client and the course staff via email, at the date specified in Table 3.1.
#### Monthly Status Reports (M1-M6)
The monthly status reports summarize the current project status, the team members' effort and project progress during a single month of the project.
Monthly status reports were delivered via email to the course staff, project members and the client at the dates specified in Table 3.1.
### Qt Implementation of the Tool (C1)
The Qt implementation of the tool is the most important project deliverable, providing the software developed during the project. It was delivered to the client at the end of the project through version control.
### Presentations
#### Project Plan Presentation (P1)
The project plan presentation was presented in a seminar at the start of the project. It was a presentation form summary of this document, intended to provide other students attending the course with a clear view of the starting point of the project.
#### Final Report Presentation and Live Demonstration (P2)
The final presentation was presented in a seminar at the end of the project. It summarized the information of the final report, as well as provided a chance to demonstrate the final system implementation.
## Planned Timetable
The planned timetable is shown in Table 3.2.
Table 3.2: Planned timetable.
The project was divided into seven main tasks: functional specification, technical specification, algorithm implementation, UI implementation, general implementation, testing and reporting. The main tasks were further divided into sub-tasks according to Table 3.2. The project was planned to be finished by week 16/2013.
# Realized project implementation

## Implementation Steps
The project was carried out in five distinct steps: functional specification, technical specification, implementation, integration and testing.
### Functional Specification
The features for the dependency analysis tool were designed in the functional specification phase. This phase consisted of several group and client meetings to find out the core features that are essential for the tool. A functional specification document was written as the result of this phase.
### Technical Specification
Technical details were defined in the technical specification phase to a technical specification document. The most important result from this phase was the architecture diagram that was drawn as a UML diagram. The technical specification phase was conducted quite promptly in order to start the implementation as early as possible. Thus, the architecture diagram was used only as a starting point and it would evolve while the implementation proceeds.
### Implementation
The actual tool was developed in the implementation phase. Development was performed in an SVN branch that was made specifically for this project. This way the development of the original Kactus2 did not interfere with the development of the tool.
The development was iterative. Group meetings were held weekly to manage the implementation and to review what was done and whether the functional specification should be somehow changed or improved. The tool was demonstrated to the client once in every two weeks to get input from the client how the tool should behave and whether its usability is going into the right direction.
Several good decisions were made during the implementation phase. It was possible to use a lot more ready-made components from Qt than was initially planned. Reuse of Qt components made it possible to get huge time savings from implementing some of the core features.
### Integration
After most of the functionality had been implemented, the integration of the tool into the main Kactus2 repository began. This consisted of a merge from the project branch to trunk and finalizing the integration with the component editor in Kactus2. Integration was straightforward and took only a week in total.
### Testing
Large-scale testing began after the integration. A test plan was written in order to execute testing in a planned way. Also, exploratory testing was used to find out special cases and scenarios where the tool would crash or otherwise behave differently than had been specified. Several bug fixes were made, and the user interface and features were fine-tuned to improve the usability of the tool.
## Deliverables
The plan for deliverables is described in section 3.3. There were some changes in the realized deliverables compared to the planned. Most of the changes were in the delivery dates, but there was one additional deliverable added to the project, as described below. Two additional monthly reports were also added as the project was longer than expected, for April (M6) and May (M7). The realized schedule for deliverables is presented in Table 4.1. For technical and functional specification (D1 and D2), the delivery date is the date of the first accepted version of the document.
### Technical Document 3 (D3): Test plan
During the implementation phase it was decided that a test plan would be written to aid in the testing process of the software. The test plan includes test cases to verify the correct functionality of the software, and additional test cases to measure the software's performance and stability.
The test plan was delivered to the client via email at the end of the project.
Table 4.1: Realized deliverables
ID	Deliverable Name	Type	Delivery Week	Recipients
D1	Functional specification	Document	2012 Wk 51	Client
D2	Technical specification	Document	2013 Wk 4	Client
D3	Test plan	Document	2013 Wk 20	Client
C1	Qt implementation of the tool	Codes	2013 Wk 17	Client
FR	Final report	Document	2013 Wk 20	Client, assistant
M1 / M2	Monthly status reports 2012 (Nov, Dec)	Document	2012 Wk 49 / 2013 Wk 2	Assistant, Client
M3 / M4 / M5 / M6 / M7	Monthly status reports 2013 (Jan, Feb, Mar, Apr, May)		2013 Wk 8 / 2013 Wk 10 / 2013 Wk 14 / 2013 Wk 19 / 2013 Wk 20	Assistant, Client
P1	Project plan presentation	Presentation	2012 Wk 48	Seminar
P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 18	Seminar

## Project Management
Joni-Matti was the project manager. He arranged meetings with the client and course staff and sent monthly reports.
The project was managed using weekly meetings and Redmine project management software at www.hostedredmine.com. The purpose of the weekly meetings was to review what had been done on the past week and what will be done in the next week. This made it significantly easier to manage the project. Redmine, on the other hand, was an effortless way to track down the time usage and the state of tasks.
### Project Meetings (internal, with the client)
Project meetings were held every week throughout the project with only a few exceptions. Client meetings where planned to be held twice a month, however especially in the implementation phase this was not true, and there were quite a few less meetings than planned. Date and contents are specified for each significant meeting in table XX.
Table 4.2: Summary of significant meetings.
Meeting	Date	Contents
Client 1/2012	1.11.2012	- First meeting with the client. Project planning / - Features for the tool planned
Team 1/2012	8.11.2012	- Project planning based on the first client meeting / - Project schedule planned out
Team 3/2012	21.11.2012	- Project plan about finished / - Work starting on functional specification / - UI mockup drawn, a lot of features planned
Client 2/2012	22.11.2012	- Work started on functional specification, primarily discussion and planning on the tool features
Client 3/2012	3.12.2012	- First draft of the UI presented to the client / - Feature planning for the functional specification
Team 9/2012	17.12.2012	- First version of functional specification to be sent to client / - Work to start on the technical specification
Team 2/2013	16.1.2013	- Technical specification can be sent to the client / - Work will start on implementation
Client 1/2013	22.2.2013	- Implementation has started, current version of the tool presented to the client / - Clarifying current features, some additional features planned / - Decision made to write a test plan for the software
Team 12/2013	3.4.2013	- Implementation is done feature-wise, tool to be integrated to the trunk of Kactus2 SVN.
Team 13/2013	10.4.2013	- Tool integrated to Kactus2 trunk / - Work to start on final report and final presentation.
Client 3/2013	11.4.2013	- Software is nearly ready feature-wise, demonstrated to the client

### Monthly Reports
Status reports of the project were delivered each month on dates specified in table 4.3. Monthly reports can be found from appendices.
Table 4.3: Monthly status reports.
Month	Delivery date	Recipients
November	07.12.2013	Course staff, client
December	13.01.2013	Course staff, client
January	18.02.2013	Course staff, client
February	08.03.2013	Course staff, client
March	05.04.2013	Course staff, client
April	12.05.2013	Course staff, client
May	20.05.2013	Course staff, client

### Inspections
Results and the progress of the project were presented to the client usually twice a month. No other inspections were made.
## Timetable and Workload
The realized timetable is shown in Table 4.4.
Table 4.4: The realized timetable.

The monthly time usage of the project is illustrated in Figure 4.1.

Figure 4.1: Monthly time usage.
The working hour distribution for each task is shown in Figure 4.2.

Figure 4.2: Working hour distribution.

## Budget
Table 4.5 summarizes the cost structure.
The majority of the project's cost came from the team's salaries and additional employee costs, which accounted for over 87% of the total expenses of the project.
Table 4.5: Cost summary

The equipment and software were leased for duration of the project. The leasing costs of equipment totaled to 450 euros for three computers and six months. The lasing costs for Visual Studio cost 360 euros for six months of use. No other equipment or licences were used during project.
Travel costs included cost of traveling to group and client meetings. In project plan travel costs to client meetings were accidentally excluded from the estimate.
Project's overall cost was 59% of the estimated cost. Reason for this was the over-estimation of needed working hours. These are explained in greater detail in chapters 4.4 and 5.1.
# Project Conclusions

## Planned Project vs. Realized Project
The implementation was finished on schedule (on week 15/2013). However, the post-project tasks, such as testing and writing the final report made the project to end a month later than what was planned.
The realized time usage differed significantly from the planned time schedule, since the project team was able to finish individual tasks in less time than was planned. The project was finished in only 52 % of time compared to the planned working hours. One large reason for this was implementation decisions made during the project. When the time estimates were made, it was assumed that the table-style widget would have to be made from scratch, but during the implementation phase, it turned out that QTreeView class can be customized to fit to the project needs. This single decision saved at least 50 hours of work. Additional small implementation decisions also caused time savings during the project, summing up to 80 hours of savings in total. The rest of the difference between the planned and realized time usage is explained by simply overestimating the time usage at the beginning. For example, group meetings took less time on the second half of the project since there were not so many things to solve and agree than in the beginning of the project.
There were two risks that came true: sickness and server downtime. Joni-Matti was ill for about two weeks at the beginning of year 2013. This resulted in a delay of one week to the planned schedule, since the implementation phase could not be started before the architecture and technical specification was ready. Fortunately, this delay was compensated during the implementation phase by the implementation decisions that offered huge time savings.
Another realized risk was that Sourceforge and Redmine were sometimes down. Since Sourceforge was used as the version control, it was not possible to commit code or retrieve newest version of the code during the downtime. However, these downtime periods were temporary and usually were fixed in a matter of hours, so they did not cause any impacts to the development. Redmine was down only once during the project, but it remained offline for almost one full day. This, however, did not have any impact on the project since the implementation could be continued without access to the project management software.
The successfulness of the realized project is tabulated in Table 5.1 as percentages compared to the planned one.
Table 5.1: Completion percentage of the project.
All project objectives (results)	100%
Budget	59%
Working hours	52%

## Future Development Needs
The project was, as it was planned, fully completed. However, a usability study will be required to determine the tool's actual usability in real-life usage scenarios by its target audience.
In addition, several ideas that did not fit into the scope of the project came up during the project, and they may be implemented to further develop the tool. These include:
- Automatic dependency descriptions for automatic dependencies.
- Handling files that exist in FileSets but are not added in the dependency analysis source directories.
- Showing dependencies from/to selected file.
- Component-specific, portable settings.

# Project Results (Technical)

## Results
The main technical result of the project is the actual software developed. The software was delivered as C++ source code, using the version control system provided by the client. Over 6 000 lines of software code were produces during the project.
The finished tool is of good quality. It does not have any problems with stability, responsiveness or performance that would hinder its everyday use. The client is happy of the tool's usability, though some additional research, such as user studies, is required to fully assess it.
# Expected Credit Units

## Expected Credit Units
The amount of time used on the project was 340 working hours. Adding the hours from the lectures (10 lectures, 60 hours for three group members in total), the total for the project work course sums up to 400 hours. This gives approximately 4.9 credit units when divided by three persons and one credit unit being 27 hours of work. Course TKT-2527 Project work gives 6-10 cp.
Since the client was really satisfied how to project progressed and the quality of the project and the implemented tool was good, client proposed 7 cp for this course. Also, the one extra point would help Mikko in his studies, since he is missing one point from the Masters degree. Thus, the expected credit units are determined to be 7 cp.
# Comments and Opinions on the Course

It was hard to reach the assistant in the course since he was so much abroad. Due to this, the project group held only meeting with the assistant. However, it did not have any negative effect on the project, since the group managed the project well without extra guidance.
# References

IEEE 1685: IP-XACT, Standard for packaging, integrating, and reusing IP within flow tools. USA 2009. Available at: http://standards.ieee.org/getieee/1685/download/1685-2009.pdf
# Appendices

## Minutes of the Meetings with the Client
## Minutes of the Internal Meetings of the Project Group
## Copies of Monthly Reports
## Copy of the Latest Approved Project Plan
## Functional Specification
## Technical Specification
## Test Plan