## Montly Report
ID	Task name	Planned running	Realized running	Status	Comments(changes, delays)		ID	Deliverable name	Type	Planned / Delivery	Realized / Delivery	Comments(changes, delays)			2012-11	2012-12	2013-1	2013-2	2013-3	2013-4			Joni-Matti	Mikko	Tommi	Total		ID	Task name	Planned / Hours	Realized / Hours	% realized	Status	Comments(changes, delays)
T1	Functional specification	46/2012 – 50/2012					D1	Functional specification	Document	2012 Wk 50				Planned hours per month	63	59	182	159	103	53		Planned hours for whole project				619		T1	Functional specification	60
T2	Technical specification	50/2012 – 2/2013					D2	Technical specification	Document	2013 Wk 2				Realized hours per month								Realized hours for whole project						T2	Technical specification	50
T3	Algorithm implementation	2/2013 – 10/2013					C1	Qt implementation of the tool	Code	2013 Wk 15				% realized	0%							% of total hours per person						T3	Algorithm implementation	77
T3.1	Dependency analysis algorithm interface	2/2013 – 3/2013					FR	Final report	Document	2013 Wk 16				Planned hours cumulative total	63	122	304	463	566	619								T3.1	Dependency analysis algorithm interface	6
T3.2	C++ dependency analysis algorithm	2/2013 – 6/2013					M1	Monthly status report	Document	2012 Wk 49				Realized hours cumulative total	0	0												T3.2	C++ dependency analysis algorithm	20
T3.3	C++ hash calculation	2/2013 – 3/2013					M2	Monthly status report	Document	2013 Wk 2				% realized of cum. Total	0							Working hours per group member						T3.3	C++ hash calculation	8
T3.4	Dependency parser settings	2/2013 – 6/2013					M3	Monthly status report	Document	2013 Wk 6																		T3.4	Dependency parser settings	10
T3.5	VHDL dependency analysis algorithm	6/2013 – 10/2013					M4	Monthly status report	Document	2013 Wk 10																		T3.5	VHDL dependency analysis algorithm	25
T3.6	VHDL hash calculation	6/2013 – 10/2013					M5	Monthly status report	Document	2013 Wk 14				Working hours of the group														T3.6	VHDL hash calculation	8
T4	UI implemementation	2/2013 – 13/2013					P1	Project plan presentation	Presentation	2012 Wk 48	2012 Wk 48																	T4	UI implemementation	170
T4.1	Basic table-style widget	2/2013 – 6/2013					P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 16																		T4.1	Basic table-style widget	50
T4.2	Dependency graph visualization	4/2013 – 10/2013																										T4.2	Dependency graph visualization	70
T4.3	Manual dependencies	6/2013 – 10/2013																										T4.3	Manual dependencies	15
T4.4	Locking dependencies	6/2013 – 10/2013						Status of deliverables																				T4.4	Locking dependencies	10
T4.5	Filter views	10/2013 – 13-2013																										T4.5	Filter views	10
T4.6	Dependency change visualization	10/2013 – 13/2013																										T4.6	Dependency change visualization	15
T5	General implementation	2/2013 – 13/2013																										T5	General implementation	30
T5.1	Folder and file scanning	2/2013 – 4/2013																										T5.1	Folder and file scanning	5
T5.2	Saving graph data in XML	4/2013 – 7/2013																										T5.2	Saving graph data in XML	25
T6	Testing	2/2013 – 13/2013																										T6	Testing	80
T7	Reporting	46/2012 – 16/2013																										T7	Reporting	152
T7.1	Group meetings	46/2012 – 15/2013																										T7.1	Group meetings	60
T7.2	Client meetings	46/2012 – 15/2013																										T7.2	Client meetings	30
T7.3	Assistant meetings	48/2012 – 16/2013																										T7.3	Assistant meetings	10
T7.4	Project plan presentation	46/2012 – 48/2012																										T7.4	Project plan presentation	12
T7.5	Final presentation	14/2013 – 16/2013																										T7.5	Final presentation	15
T7.6	Final report	14/2012 – 16/2013																										T7.6	Final report	25
																												Total hours		619
																																					Planned	Realized	%
	Status of tasks																																			Project results achieved
																													Working hours per task							Calendar weeks
																																				Person hours
																																				Budget

																																				summary vs project

## Task Summary
ID	Task name	Running weeks	Allocated hours	% of total hours	Related deliverables
T1	Functional specification	46/2012 – 50/2012	60	9,1	Functional specification
T2	Technical specification	50/2012 – 2/2013	50	7,59	Technical specification
T3	Algorithm implementation	2/2013 – 10/2013	77	11,68	Final code
T3.1	Dependency analysis algorithm interface	2/2013 – 3/2013	6	0,91
T3.2	C++ dependency analysis algorithm	2/2013 – 6/2013	20	3,03
T3.3	C++ hash calculation	2/2013 – 3/2013	8	1,21
T3.4	Dependency parser settings	2/2013 – 6/2013	10	1,52
T3.5	VHDL dependency analysis algorithm	6/2013 – 10/2013	25	3,79
T3.6	VHDL hash calculation	6/2013 – 10/2013	8	1,21
T4	UI implemementation	2/2013 – 13/2013	170	25,8	Final code
T4.1	Basic table-style widget	2/2013 – 6/2013	50	7,59
T4.2	Dependency graph visualization	4/2013 – 10/2013	70	10,62
T4.3	Manual dependencies	6/2013 – 10/2013	15	2,28
T4.4	Locking dependencies	6/2013 – 10/2013	10	1,52
T4.5	Filter views	10/2013 – 13-2013	10	1,52
T4.6	Dependency change visualization	10/2013 – 13/2013	15	2,28
T5	General implementation	2/2013 – 13/2013	30	4,55	Final code
T5.1	Folder and file scanning	2/2013 – 4/2013	5	0,76
T5.2	Saving graph data in XML	4/2013 – 7/2013	25	3,79
T6	Testing	2/2013 – 13/2013	80	12,14
T7	Reporting	46/2012 – 16/2013	192	29,14
T7.1	Group meetings	46/2012 – 15/2013	60	9,1	Meeting memos
T7.2	Client meetings	46/2012 – 15/2013	30	4,55	Meeting memos
T7.3	Assistant meetings	48/2012 – 16/2013	10	1,52	Meeting memos
T7.4	Project plan presentation	46/2012 – 48/2012	12	1,82	Project plan presentation
T7.5	Final presentation	14/2013 – 16/2013	15	2,28	Final presentation
T7.6	Final report	14/2013 – 16/2013	25	3,79	Status reports, memos
T7.7	Other reports	46/2012 – 15/2013	40	6,07	Final report
	Total	46/2012 – 15/2013	659

## TaskSchedule
ID	Task name	2012-11 (63)				2012-12 (69)				2013-01 (172)					2013-02 (159)				2013-03 (103)				2013-04 (53)			Hours per task		ID	Task name	2012-11 (63)				2012-12 (59)				Hours per task 2012			ID	Task name	2013-01 (182)					2013-02 (159)				2013-03 (103)				2013-04 (53)			Hours per task 2013					Running weeks	Allocated hours	% of total hours	Related deliverables
		45	46	47	48	49	50	51	52	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16					45	46	47	48	49	50	51	52					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16
T1	Functional specification		12	12	12	12	12					60		T1	Functional specification		12	12	12	12	12			60			T1	Functional specification					0					46/2012 – 50/2012	60	12	Functional specification
T2	Technical specification					10	10	10	10	10					50		T2	Technical specification					10	10	0	20			T2	Technical specification	18	12					30					50/2012 – 2/2013	50	10	Technical specification
T3.1	Dependency analysis algorithm interface					3	3					6		T3.1	Dependency analysis algorithm interface					0			T3.1	Dependency analysis algorithm interface		3	3					6					2/2013 – 3/2013	6	Err:509
T3.2	C++ dependency analysis algorithm					4	4	4	4	4					20		T3.2	C++ dependency analysis algorithm					0			T3.2	C++ dependency analysis algorithm		4	4	4	4	4					20					2/2013 – 6/2013	20	Err:509
T3.3	C++ hash calculation					4	4					8		T3.3	C++ hash calculation					0			T3.3	C++ hash calculation		4	4					8					2/2013 – 3/2013	8	Err:509
T3.4	Dependency parser settings					2	2	2	2	2					10		T3.4	Dependency parser settings					0			T3.4	Dependency parser settings		2	2	2	2	2					10					2/2013 – 6/2013	10	Err:509
T3.5	VHDL dependency analysis algorithm					5	5	5	5	5					25		T3.5	VHDL dependency analysis algorithm					0			T3.5	VHDL dependency analysis algorithm					5	5	5	5	5					25					6/2013 – 10/2013	25	Err:509
T3.6	VHDL hash calculation					1	1	2	2	2					8		T3.6	VHDL hash calculation					0			T3.6	VHDL hash calculation					1	1	2	2	2					8					6/2013 – 10/2013	8	Err:509
T4.1	Basic table-style widget					10	10	10	10	10					50		T4.1	Basic table-style widget					0			T4.1	Basic table-style widget		10	10	10	10	10					50					2/2013 – 6/2013	50	Err:509
T4.2	Dependency graph visualization					10	10	10	10	10	10	10					70		T4.2	Dependency graph visualization					0			T4.2	Dependency graph visualization				10	10	10	10	10	10	10					70					4/2013 – 10/2013	70	11,67
T4.3	Manual dependencies					3	3	3	3	3					15		T4.3	Manual dependencies					0			T4.3	Manual dependencies					3	3	3	3	3					15					6/2013 – 10/2013	15	Err:509
T4.4	Locking dependencies					2	2	2	2	2					10		T4.4	Locking dependencies					0			T4.4	Locking dependencies					2	2	2	2	2					10					6/2013 – 10/2013	10	Err:509
T4.5	Filter views					3	2	2	3				10		T4.5	Filter views					0			T4.5	Filter views					3	2	2	3				10					10/2013 – 13-2013	10	Err:509
T4.6	Dependency change visualization					3	4	4	4				15		T4.6	Dependency change visualization					0			T4.6	Dependency change visualization					3	4	4	4				15					10/2013 – 13/2013	15	Err:509
T5.1	Folder and file scanning					2	1	2					5		T5.1	Folder and file scanning					0			T5.1	Folder and file scanning		2	1	2					5					2/2013 – 4/2013	5	Err:509
T5.2	Saving graph data in XML					6	6	6	7					25		T5.2	Saving graph data in XML					0			T5.2	Saving graph data in XML				6	6	6	7					25					4/2013 – 7/2013	25	Err:509
T6	Testing					4	4	4	4	6	6	6	8	8	10	10	10				80		T6	Testing					0			T6	Testing		4	4	4	4	6	6	6	8	8	10	10	10				80					2/2013 – 13/2013	80	Err:509
T7.1	Group meetings		3	3	3	3	3	3			3	3	3	3	3	3	3	3		60		T7.1	Group meetings		3	3	3	3	3	3		18			T7.1	Group meetings		3	3	3	3	3	3	3	3		42					46/2012 – 15/2012	60	Err:509	Meeting memos
T7.2	Client meetings			3		3		3				3		3		3		3		3		3		3		30		T7.2	Client meetings			3		3		3		9			T7.2	Client meetings			3		3		3		3		3		3		3		21					46/2012 – 15/2012	30	Err:509	Meeting memos
T7.3	Assistant meetings				3					3					4			10		T7.3	Assistant meetings				3					3			T7.3	Assistant meetings				3					4			7					48/2012 – 16/2012	10	Err:509	Meeting memos
T7.4	Project plan presentation		2	4	6					12		T7.4	Project plan presentation		2	4	6					12			T7.4	Project plan presentation					0					46/2012 – 48/2012	12	Err:509	Project plan presentation
T7.5	Final presentation					3	6	6	15		T7.5	Final presentation					0			T7.5	Final presentation					3	6	6	15					14/2012 – 16/2012	15	Err:509	Final presentation
T7.6	Final report					5	10	10	25
T7.7	Other reports		1	1	1	5	1	1			5	1	1	1	5	1	1	1	4	1	1	1	5	1	1	40		T7.6	Final report					0			T7.7	Final report					5	10	10	25					14/2012 – 16/2012	25	Err:509	Final report
	Hours per week	0	18	23	25	23	26	17	10	10	47	35	45	43	57	41	32	37	43	23	20	24	20	23	17	659		T7.7	Other reports		1	1	1	5	1	1		10			T7.7	Other reports		5	1	1	1	5	1	1	1	4	1	1	1	5	1	1	30					46/2012 – 15/2012	Err:509
	Deliverables					D1				D2					C1	FR				Hours per week	0	18	23	25	23	26	17	0	132				Hours per week	18	49	35	45	43	57	41	32	37	43	23	20	24	20	23	17	527
	Meetings				A1					A2					A3					Deliverables					D1					Deliverables		D2					C1	FR
				Meetings				A1					Meetings				A2					A3

				LEGEND
				ID	Meetings/Reviews	Attendance	Notes
				A1	Milestone meeting 1	Assistant, group
				A2	Milestone meeting 2	Assistant, group
				A3	Milestone meeting 3	Assistant, group
				ID	Deliverable	Delivery recipients	Notes
				D1	Functional specification	Client, assistant
				D2	Technical specification	Client, assistant
				C1	Qt implementation of the tool	Client
				FR	Final report	Client, assistant
				M1	Monthly status reports 2012 (Nov, Dec)	Assistant
				M2
				M3	Monthly status reports 2013 (Jan, Feb, Mar)	Assistant
				M4
				M5
				P1	Project plan presentation	Seminar
				P2	Final report presentation and live demonstration	Seminar

## Task Costs
Project costs (personal example)
					ID	Task name	Allocated hours	Task cost
type of expense:					T1	Functional specification	60	840 €
Personnel costs					T2	Technical specification	50	700 €
Working hours	650			Salary after taxes?		T3	Algorithm implementation	77	1 078 €
Salary per hour	14 €			8 €		T3.1	Dependency analysis algorithm interface	6	84 €
Salaries for project	9 100 €			5 460 €		T3.2	C++ dependency analysis algorithm	20	280 €
Indirect employee costs	3 640 €	40 %		1 820 €		T3.3	C++ hash calculation	8	112 €
Personnel costs total	12 754 €					T3.4	Dependency parser settings	10	140 €
					T3.5	VHDL dependency analysis algorithm	25	350 €
Travel	50 €	VAT excluded				T3.6	VHDL hash calculation	8	112 €
Equipment	375 €					T4	UI implemementation	170	2 380 €
Licences	300 €					T4.1	Basic table-style widget	50	700 €
Consumables and material	50 €					T4.2	Dependency graph visualization	70	980 €
Subcontracting	0 €					T4.3	Manual dependencies	15	210 €
Other costs	75 €	Leasing käsittelykulut				T4.4	Locking dependencies	10	140 €
Other costs total	850 €					T4.5	Filter views	10	140 €
					T4.6	Dependency change visualization	15	210 €
Total project expences	13 604 €					T5	General implementation	30	420 €
Profit	0 €	0 %				T5.1	Folder and file scanning	5	70 €
Price of the project	13 604 €					T5.2	Saving graph data in XML	25	350 €
Price of the project (vat 23% inc)	16 733 €					T6	Testing	80	1 120 €
					T7	Reporting	192	2 688 €
					T7.1	Group meetings	60	840 €
VAT is different for different cost types (travel, equipment)					T7.2	Client meetings	30	420 €
					T7.3	Assistant meetings	10	140 €
					T7.4	Project plan presentation	12	168 €
					T7.5	Final presentation	15	210 €
					T7.6	Final report	25	350 €
					T7.7	Other reports	40	560 €
					Total	659	9 226 €