Project Plan
Dependency Analysis Tool
for Kactus2
Version 0.98

TUT	Department of Computer Systems	TKT-2527 Project Work
Author: Joni-Matti Määttä
Joni-Matti Määttä, joni-matti.maatta@tut.fi
Mikko Honkonen, mikko.honkonen@tut.fi
Tommi Korhonen, tommi.korhonen@tut.fi

Document State: Work-in-progress		Modified: 2012-11-21

Version History

Version	Date	Author(s)	Summary of Changes
0.1	2012-10-14	J.-M. Määttä	Modified the document base and headers.
0.2	2012-10-16	J.-M. Määttä, M. Honkonen, T. Korhonen	Added some content to all chapters.
0.3	2012-10-23	M. Honkonen	Introduction and project objectives just about done.
0.4	2012-10-23	J.-M. Määttä	Added project background, project management information and information about the used tools and environment. Not fully ready though.
0.45	2012-10-24	T. Korhonen	Added tables and some content to implementation and budget.
0.5	2012-10-24	J.-M. Määttä, M. Honkonen, T. Korhonen	Additional improvements to all chapters.
0.6	2012-11-01	M. Honkonen	Task descriptions in Chapter 6.
0.7	2012-11-08	J.-M. Määttä, M. Honkonen, T. Korhonen	General perfections and clean up for all chapters.
0.8	2012-11-13	M. Honkonen	Task table and summaries added.
0.9	2012-11-13	J.-M. Määttä	Added the executive summary and more about risks in Chapter 8
0.95	2012-11-14	T. Korhonen	Tables for task schedule and budget added.
0.96	2012-11-19	T. Korhonen	Divided the task schedule table and added explanations for the project costs.
0.97	2012-11-20	M. Honkonen	Fixed formatting for task table, fixed formatting problems in chapter 7.
0.98	2012-11-21	J.-M. Määttä	Added more about risks in Chapter 8.

Executive Summary

Kactus2 is an open-source IP-XACT-based EDA tool developed at Tampere University of Technology. It aims for easier product management and development than any other tool on the market, including commercial ones. Dependency management is an essential requirement for any tool which deals with HW projects consisting even of thousands of source files. Managing such projects becomes extremely hard if the tool does not offer any help for managing dependencies between the source files. This is important especially when source modifications are made to be able to keep the whole project in compilable form at all times.
The purpose of this project is to develop a dependency analysis tool that integrates with Kactus2 and offers various advantages compared to other EDA tools. The tool will be able to handle dependencies between C, C++ and VHDL files automatically and manually between other files. The project group consists of three persons with varying backgrounds in software development. The project is estimated to take five months.
Table of Contents

# Introduction

## Overview
Dependency analysis tool for Kactus2 project is is made for Tampere University of Technology as a project work for course TKT-2527. The purpose of the project is to develop a dependency analysis tool to manage dependencies between various different files in a hardware project. The tool is to be integrated with Kactus2 which is being developed at the Department of Computer Systems at Tampere University of Technology. The project group consists of three persons with varying backgrounds in software development. The project is estimated to take five months.
## Target and Scope of the Document
This document is the project plan for the dependency analysis tool for Kactus2 project. The document gathers all the necessary information for the team to start working on the project. In this document the project is divided into various tasks, and the project schedule is agreed upon.
The document also provides information to the client, and the client's acceptance for the document is required to proceed with the project. In addition, the document provides the course staff information about the project.
## Structure of the Document
This document is divided into 10 chapters as follows:
1. Introduction. This chapter, acts as an introduction to the document.
2. Project background description. Describes the purpose of the project and its technical background.
3. Project organization. Information about the project team, client and other interest groups of the project.
4. Project objectives. Describes the various objectives that are to be achieved during the project.
5. Project resources. The tools and environments used during the project, as well as any other resources needed for the project.
6. Implementation. Here the project is divided into tasks, the tasks are scheduled and they are assigned to the project team members.
7. Budget. The project budget is described in this chapter.
8. Project management. Description about how the project is managed and controlled.
9. References.
10. Appendices.
# Project Background Description

## Overview
Large-scale embedded HW projects require thousands of files, which becomes a nightmare to manage without proper tools. The most challenging aspect with a large amount of files is managing dependencies between files to prevent accidentally breaking the source by modifications.
Kactus2 is an open-source IP-XACT-based EDA tool which aims for easier product management and development. It is developed in TUT, in the Department of Computer Systems. Dependency management is an essential requirement for having an improved workflow in Kactus2.
## Purpose of the Project
The purpose of the project is to create a dependency analysis tool for Kactus2 in order to resolve dependencies between various source files related to a hardware project. Within the scope of this project, the dependency analysis tool must be able to resolve dependencies between C, C++ and VHDL source files, visualize file relations using a special table-graph notation and allow relations to be added manually between any files.
## Technological Background
Kactus2 is developed in C++ using Qt framework to allow cross-platform development. It is based on IP-XACT standard [1] which defines a way of packetizing HW components and related metadata using an XML-based file format.
The project is hosted in SourceForge. Windows and Linux distributions are actively kept up to date.

# Project Organization

## Project Members
The project consists of three members:
Joni-Matti Määttä
joni-matti.maatta@tut.fi
Joni-Matti is the project managaer and SW architect in the project.
Mikko Honkonen
mikko.honkonen@tut.fi
Mikko is the test lead in the project. He is also responsible of major development tasks in the project.
Tommi Korhonen
tommi.korhonen@tut.fi
Tommi is the UI specialist in the project. He also does software development in the project.
All members in the project group take part in writing the documentation for the project. Joni-Matti is in charge of the project plan and technical specification document. Tommi is in charge of the functional specification document. Mikko is in charge of the testing plan.
## Client
Timo D. Hämäläinen (timo.d.hamalainen@tut.fi) is the client of the project.
## Other Interest Groups
Other interest groups include the TKT-2527 Project Work course staff, Kactus2 development team and end users. Monthly reports will be done for the course staff about the progress of the project. All project documents will also be sent to the course staff. The original Kactus2 development team is informed about any large decisions made in the project so that integrating the final product into Kactus2 is as effortless as possible.

# Project Objectives
## Definition of Objectives
### The Objectives of Different Interest Groups
The objectives of the project group are:
- To finish a whole software development project in schedule (required)
- To have a working product integrated into Kactus2 (requested)
- Learn about project management and scheduling (requested)
The objectives of the client are:
- The dependency analysis tool should have at least as good usability as Kactus2 itself (requested)
- The tool should improve the user experience and offer features that truly make the use easier (requested)
- The tool should be well integrated into Kactus2 so that it does not look like a part of its own (required)
### Technical Objectives
The technical objective of the project is to develop good, modular software component that is easy to integrate into any Qt-based application (requested).
## Deliverables
Table 4.1 summarizes all project deliverables.
Table 4.1: Project deliverables.
ID	Deliverable Name	Type	Delivery Week	Recipients
D1	Functional specification	Document	2012 Wk 50	Client, assistant
D2	Technical specification	Document	2013 Wk 2	Client, assistant
C1	Qt implementation of the tool	Codes	2013 Wk 15	Client
FR	Final report	Document	2013 Wk 16	Client, assistant
M1 / M2	Monthly status reports 2012 (Nov, Dec)	Document	2012 Wk 49 / 2013 Wk 2	Assistant
M3 / M4 / M5	Monthly status reports 2013 (Jan, Feb, Mar)		2013 Wk 6 / 2013 Wk 10 / 2013 Wk 14	Assistant
P1	Project plan presentation	Presentation	2012 Wk 48	Seminar
P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 16	Seminar

### Reports and Documentation
#### Technical Document 1 (D1): Functional Specification
The functional specification describes the behavior of the system from the user perspective. It specifies how the system reacts to given input, providing the team the information necessary to write the technical specification. The client is required to accept the functional specification.
The functional specification document will be delivered to the client and the course staff via email, at the date specified in Table 4.1.
#### Technical Document 2 (D2): Technical Specification
The technical specification describes the system architecture. It is written in such way that the entire system can then be implemented based only on information found in it. The technical specification is required before the system can be implemented.
The functional specification document will be delivered to the client and the course staff via email, at the date specified in Table 4.1.
#### Final Report (FR)
The final report summarizes information from the entire time span of the project, such as what the actual project schedule was in comparison to the planned, and whether or not the project reached the goals set in the project plan.
The final report will be delivered to the client and the course staff via email, at the date specified in Table 4.1.
#### Monthly Status Reports (M1-M6)
The monthly status reports summarize the current project status, the team members' effort and project progress during a single month of the project.
Monthly status reports will be delivered via email to the course staff at the dates specified in Table 4.1.
### Qt Implementation of the Tool (C1)
The Qt implementation of the tool is the most important project deliverable, providing the software developed during the project. It will be delivered to the client at the end of the project.
### Presentations
#### Project Plan Presentation (P1)
The project plan presentation will be presented in a seminar at the start of the project. It is a presentation form summary of this document, intended to provide other students attending the course with a clear view of the starting point of the project.
#### Final Report Presentation and Live Demonstration (P2)
The final presentation will be presented in a seminar at the end of the project. It summarizes the information of the final report, as well as provides a chance to demonstrate the final system implementation.
# Project Resources

## Overview
All development is performed using each team member's personal computers at home. Each team member is required to have a working Internet connection to be able to access the version control server from their apartment. The project does not require that the members need to buy any software. All software will either be free or available at Microsoft DreamSpark which grants access to TUT students at no charge.
## Tools and Environment
Table 5.1 lists all tools and libraries used in the project.
Table 5.1: The used tools in the project.
Software	Version
Adobe Photoshop	CS5 Extended
AnkhSVN	2.4
Doxygen	1.8.2
Microsoft Visual Studio 2008	Standard / Professional Edition
OpenOffice / LibreOffice	3.x
Qt	4.8.3
SlikSVN	1.7.7
StarUML	5.0
TortoiseSVN	1.7.10

The original Kactus2 code base is used as the starting point for the project. It is available in Source Forge. The dependency analysis tool will be hosted as branch to the original Kactus2 project.
The software is developed in Windows, even though it is required to be cross-platform compatible. Cross-platform tests may require the use of Linux operating system. Redmine is used as the primary project management environment, hosted at www.hostedredmine.com.
Joni-Matti is the tool correspondent for all used tools and the used environment. If, during the project, any needs for other software or new versions appears, the usage has to be approved by the tool correspondent.
# Implementation

## Overview
Project consist of different tasks some of which are divided into subtasks. These tasks are summarized on the Table 6.1.

Table 6.1: Task summary.
## Task Definitions
### T1, Functional specification
Designing, writing and reviewing the functional specification document.
### T2, Technical specification
Designing, writing and reviewing the technical specification document based on the functional specification.
### T3, Algorithm implementation
The implementation of the various systems of dependency analysis algorithms.
#### T3.1, Dependency analysis algorithm interface
Creating an interface for dependency analysis algorithms, to allow simple modular expansion of supported file types.
#### T3.2, C++ dependency analysis algorithm
Creating an algorithm which will figure out the dependency relations of given C/C++ source files.
#### T3.3, C++ hash calculation
Calculating hash function for C/C++ files.
#### T3.4, Dependency parser settings
Storing, retrieving and applying settings for dependency analysis, such as file extensions or files being ignored.
#### T3.5, VHDL dependency analysis algorithm
Creating an algorithm which will figure out the dependency relations of given VHDL source files.
#### T3.6, VHDL hash calculation
Calculating hash function for VHDL files.
### T4, UI implementation
The implementation of the various UI elements of the software.
#### T4.1, Basic table-style widget
Creating a custom Qt widget used for displaying the dependency graph.
#### T4.2, Dependency graph visualization
Presenting the dependency data of the related files to the user in useful and easily understandable manner on the created widget.
#### T4.3, Manual dependencies
Implementing the necessary features to provide the user ability to assign dependencies between files manually.
#### T4.4, Locking dependencies
Implementing the ability to manually lock dependencies so they are not removed in following automatic scans.
#### T4.5, Filter views
Implementing the ability to filter the dependency graph view on given rules, such as only showing broken dependencies.
#### T4.6, Dependency change visualization
Visualizations to show changes in dependencies after the previous run of the tool.
### T5, General implementation
The parts of implementation that do not fit directly into algorithm or UI categories.
#### T5.1, Folder and file scanning
Implementing a GUI button, which can be used to provide a directory to perform dependency analysis on. The tool then scans the directory contents recursively.
#### T5.2, Saving graph data in XML
Implementing the features required to save the dependency analysis result data in XML as IP-XACT vendor extensions.
### T6, Testing
Testing will be performed during development by the developers, but also separately to ensure that the tool is stable and works as expected in all circumstances.
### T7, Reporting
The various reporting necessary during the project, as well as meetings.
#### T7.1 Group meetings
The weekly meetings held by the project group.
#### T7.2, Client meetings
The meetings held by the project group with the client, in which project status is reviewed.
#### T7.3, Assistant meetings
The meetings held by the project group with the course assistant.
#### T7.4, Project plan presentation
Preparing for and presenting the project plan presentation at the start of the project.
#### T7.5, Final presentation
Preparing for and presenting the final presentation at the end of the project.
#### T7.6, Final report
Writing and reviewing the final report at the end of the project, summarizing the project.
## Resource Allocations to Tasks
Table 6.2 lists the responsibilities of each project group member. Used abbreviations are listed below:
- P = Participant
- R = Review
- A = Accountable
- I = Input needed
Table 6.2: Responsibilities.
Person	Joni-Matti Määttä	Mikko Honkonen	Tommi Korhonen	Client
Phase
Project Plan	A	P	P	I
Functional specification	P	P	A	P
Technical specification	A	P	P	R
Implementation	A	P	P	R
Testing	P	A	P	-

## Schedule for Each Task
Tables 6.3 and 6.4 show the schedule for years 2012 and 2013. The used abbreviations are listed in Table 6.5.

Table 6.3: Schedule for 2012.

Table 6.4: Schedule for 2013.

Table 6.5: Legend for Schedule Tables
# Budget

## Overview
Table 7.1 summarizes the costs structure.

Table 7.1: Cost summary

There is no need to purchase any licenses because all used software is either free or license is free for students. There is also no need to buy any equipment because development is performed using each member's personal computers. Consumables and material cost consist of buying paper required for printing and other supply items. Travel cost are low, because most of the development is done at each member's home and therefore there is no need to travel. However, occasional bus trips are needed to get to meeting. Majority of the project's cost comes from salary of the employees.
## Cost Allocation
Cost of each task is given in table 7.2

Table 7.2: Task specific costs
## Funding
In a real-life scenario, funding for the project would come from Tampere University of Technology. The main development of Kactus2 will be continued in a project called Metabase, scheduled to start in January 2013.
# Project Management

## Overview
The project management in this project consists of regular internal meetings, meetings with the client and the use of Redmine project management environment. In addition, Skype and e-mail are used for daily communication.
## Project Group Meeting Plan
By default, the project group meetings are held weekly. If live meetings are not required at some point, Skype is used for weekly status review. Live meetings are scheduled primarily for Wednesday at 12:30 pm. However, the final times are agreed on a week-by-week basis. The meeting location is the main lobby of Tietotalo.
## Meeting Plan with the Client
The meetings with the client are held on an as-needed basis but at least once in every month. The client is consulted more often while making functional and technical specification.
## Meeting Plan with the Course Staff
Three meetings will be held with the course staff. The first one is held at the project planning stage, the second one in the middle of the project and the last one when the project ends. The dates for the meetings are as follows:
- First meeting on xth Nov 2012
- Second meeting on xth Jan 2013
- Third meeting on xth Mar 2013
## Risks Analysis
The SWOT analysis of the risks is illustrated below:
Strengths / Joni-Matti is a part of the original Kactus2 team / Joni-Matti has experience in other projects and project management / All members have experience in C++ / The project topic is quite simple and does not require too much special skills	Weaknesses / Two members of the project group have only basic experience in Qt
Opportunities / All team members learn new skills in project management and Qt development / If Kactus2 becomes popular, the dependency analysis tool will be well-known and used by many	Threats / Joni-Matti has multiple ongoing projects at the moment

### Potential Risks
Table 8.1 lists potential risks that may realize during the project. Risks probability and severity are defined in a scale from one to three. One means the least probable and the least severe and three means the most probable and the most severe. The importance of a risk is determined as a product of probability and severity.
Table 8.1: Potential risks.
ID	Description	Probability	Severity	Importance
1	Project group member's motivation drops.	1	3	3
2	Hardware failures.	2	2	4
3	Software failures and blue-screens.	2	1	2
4	SourceForge is offline or having maintenance.	2	2	2
5	SourceForge SVN version control corrupts.	1	3	3
6	Electrical failures.	1	2	2
7	Someone gets sick.	2	2	4
8	Internet connection failures.	2	2	4

The probability of any project group member's motivation to drop during the project is quite small but still possible. The severity of that is quite high because the project group has only three members.
Hardware and software failures are nowadays rather common. From these two, hardware failures are much more severe than software failures, since software failures can usually be overcome by restarting the computer, or in a problematic case, reinstalling Windows. The delays caused by hardware failures are prevented by the fact that all members of the project group have laptops as secondary computers and can continue working with them if the desktop PCs would malfunction.
Also SourceForge maintenance can cause problems during the project. If SourceForge is down, the version control repository cannot be accessed. The solution to this is to continue work in the local working copy until SourceForge is back online. In a critical case, files may be sent by email, if working is not possible without a version control update.
Corruption of the SourceForge's Subversion version control is a serious risk. Fortunately, it is much less probable than server downtime. The consequences of version control corruption are minimized by keeping working copies available on all development computers at all times. A new repository is created from the most up-to-date working copy to continue development.
Electrical failures unlikely but may happen. Losing unsaved data is the largest consequence that electrical failures may cause. This can be prevented by saving files often.
It is probable that someone gets sick during the project. This may cause a small or a large delay to the project if the person is responsible of major parts of the software, depending on how long the person is sick. In short-term absence, no actions are made, but if the absence gets longer, tasks are reassigned appropriately.
In addition to hardware and software failures, there may be times when the Internet connections are down. In case of an Internet connection failure, the members of the project group are prepared to go working on the university with their laptops.
## Acceptance of Results
### When Will the Project End
The project will end when any of the following applies:
- The dependency analysis tool is complete and fully integrated with Kactus2
- The final ending date after one month of the planned project end date is reached
There shall be a meeting that confirms the ending of the project. The client will take part to the final meeting.
### Who Will Accept the Results
The results are accepted by the project manager, the client and the project work course staff.
### Acceptance of Changes in Project Objectives
Possible changes in the project objectives are accepted by the project manager and the client.
### Acceptance of Changes in the Project Group
The goal is to keep the project team exactly as it is now, but if some team member doesn't do his part or has to be removed from the group for some other reason, it will be decided by the project manager and the client. The same applies for the need of additional team members.
### Expected Credit Units
Taking the project size into account, the expected credit units are determined to be 7 cp.

# References

IEEE 1685: IP-XACT, Standard for packaging, integrating, and reusing IP within flow tools. USA 2009. Available at: http://standards.ieee.org/getieee/1685/download/1685-2009.pdf
# Appendices

## Minutes of the Meetings with the Client
## Minutes of the Internal Meetings of the Project Group
## Functional and Technical Specifications, if Relevant
## Other