Project status report M1
Delivery 2013 Wk 7

# Dependency Analysis for Kactus2

Reporting period:	2013 January (Wk 1 – Wk 5)

Project group:	Joni-Matti Määttä	joni-matti.maatta@tut.fi
Mikko Honkonen	mikko.honkonen@tut.fi
Tommi Korhonen	tommi.korhonen@tut.fi

Delivery: Joni-Matti Määttä, Mikko Honkonen, Tommi Korhonen, Timo D. Hämäläinen, Marko Hännikäinen, Francescantonio Della Rosa

## 1. Description of work
The initial version of the technical specification was finished and the implementation phase begun.

1.1. Results achieved
Technical specification

1.2. Problems encountered
-

1.3. Changes to the project plan
-

1.4. Immediate actions needed
More hours should be spent to the project.

## 2. Status of Tasks (finishing wk 52, the last week of this reporting period)
## 3. Status of Deliverables (finishing wk 52, the last week of this reporting period)
## 4. Usage Statistics (finishing wk 52, the last week of this reporting period)

4.1. Working hours of the group
* Planned for complete project: 659 h person hours total

4.2. Working hours per group member

4.3. Working hours per task

## 5. Summary vs. whole project

	Planned	Realized	%
Project results achieved / (not number of deliverables or similar simple metric)	Qualitative, subjective / self-assessment		30%
Calendar weeks / (on the timeline from beginning wk to end wk)	24 wk	13 wk	54%
Person hours	659 h	110,60 h	17%
Budget	16 733 €	2808 €	17%

Task Table in the Project plan:

Deliverables Table in the Project plan:

ID	Deliverable Name	Type	Delivery Week	Recipients
D1	Functional specification	Document	2012 Wk 50	Client, assistant
D2	Technical specification	Document	2013 Wk 2	Client, assistant
C1	Qt implementation of the tool	Codes	2013 Wk 15	Client
FR	Final report	Document	2013 Wk 16	Client, assistant
M1 / M2	Monthly status reports 2012 (Nov, Dec)	Document	2012 Wk 49 / 2013 Wk 2	Assistant
M3 / M4 / M5	Monthly status reports 2013 (Jan, Feb, Mar)		2013 Wk 6 / 2013 Wk 10 / 2013 Wk 14	Assistant
P1	Project plan presentation	Presentation	2012 Wk 48	Seminar
P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 16	Seminar

Schedule Chart in the Project plan: