## Sheet1
| Nov 2012 | Dec 2012 | Jan 2013 | Feb 2013 | Mar 2013 | Apr 2013 | ID | Task | Planned | Realized
Planned | 66 | 66 | 190 | 167 | 110 | 60 | T7 | Reporting | 192 | 85.3
Realized | 26.35 | 34.85 | 49.4 | 62.85 | 93.05 | 35 | T6 | Testing | 80 | 35
[7 empty] | T5 | General Implementation | 30 | 19
[7 empty] | T4 | UI Implementation | 170 | 84.25
[7 empty] | T3 | Algorithm Implementation | 77 | 37.75
[7 empty] | T2 | Technical Specification | 50 | 11.35
[7 empty] | T1 | Functional Specification | 60 | 29.35