Project status report M1
Delivery 2012 Wk 49

# Dependency Analysis for Kactus2

Reporting period:	2012 November (Wk 44 – Wk 48)

Project group:	Joni-Matti Määttä	joni-matti.maatta@tut.fi
Mikko Honkonen	mikko.honkonen@tut.fi
Tommi Korhonen	tommi.korhonen@tut.fi

Delivery: Joni-Matti Määttä, Mikko Honkonen, Tommi Korhonen, Timo D. Hämäläinen, Marko Hännikäinen, Francescantonio Della Rosa

## 1. Description of work
The team finished the first complete version of the project plan and began working on the functional specification. Multiple meetings with the client were held to collect information about the requirements of the dependency analysis tool. In the project group's internal meetings, the first UI draft for the tool was designed (to be included in the functional specification).

1.1. Results achieved
Project plan and some content to the functional specification, including the first UI draft.

1.2. Problems encountered
None.

1.3. Changes to the project plan
None (first version made).

1.4. Immediate actions needed
None.

## 2. Status of Tasks (finishing wk 48, the last week of this reporting period)
## 3. Status of Deliverables (finishing wk 48, the last week of this reporting period)

## 4. Usage Statistics (finishing wk 48, the last week of this reporting period)

4.1. Working hours of the group
* Planned for complete project: 619 h person hours total

4.2. Working hours per group member

4.3. Working hours per task

## 5. Summary vs. whole project

	Planned	Realized	%
Project results achieved / (not number of deliverables or similar simple metric)	Qualitative, subjective / self-assessment		5%
Calendar weeks / (on the timeline from beginning wk to end wk)	24 wk	4 wk	16%
Person hours	619 h	26,35 h	4%
Budget	1 000 €	0 €	0%

Task Table in the Project plan:

Deliverables Table in the Project plan:

ID	Deliverable Name	Type	Delivery Week	Recipients
D1	Functional specification	Document	2012 Wk 50	Client, assistant
D2	Technical specification	Document	2013 Wk 2	Client, assistant
C1	Qt implementation of the tool	Codes	2013 Wk 15	Client
FR	Final report	Document	2013 Wk 16	Client, assistant
M1 / M2	Monthly status reports 2012 (Nov, Dec)	Document	2012 Wk 49 / 2013 Wk 2	Assistant
M3 / M4 / M5	Monthly status reports 2013 (Jan, Feb, Mar)		2013 Wk 6 / 2013 Wk 10 / 2013 Wk 14	Assistant
P1	Project plan presentation	Presentation	2012 Wk 48	Seminar
P2	Final report presentation and live demonstration	Presentation + demo	2013 Wk 16	Seminar

Schedule Chart in the Project plan: