## Slide 1: Dependency Analysis for Kactus2
Final Presentation

## Slide 2: Outline
Project Organization
Project Background & Objectives
What was done?
Problems Met and Solutions
Realized Risks
Time Usage
What did we learn?
Conclusion

## Slide 3: Project Organization
Project team
  Joni-Matti Määttä (project manager, SW architect, developer)
  Mikko Honkonen (test lead, developer)
  Tommi Korhonen (UI specialist, developer)
Client
  Timo D. Hämäläinen
Course staff
  Marko Hännikäinen
  Francescantonio Della Rosa

## Slide 4: Project Background (1)
Kactus2
  Developed at TUT
  Open-source toolset to design embedded products, especially FPGA-based MP-SoCs
  Based on IP-XACT XML metadata and design methodology
Kactus2 goals
  Easier IP reusability
  Practical HW/SW abstraction for easier application SW development
  The most user-friendly EDA tool

## Slide 5: Project Background (2)
file2
file3
file5
file4
file1
C++
Compilation errors are often caused by missing dependent files or libraries
  As project size increases, it becomes more and more difficult to keep track of these file dependencies
Solution: automate file dependency tracking by scanning supported files and keeping track of file changes
  Allow also manual dependencies between e.g. source code and documentation
VHDL
C++
Dependency
Analysis
Tool

## Slide 6: Objectives
Objectives of the project group
  Finish a whole software development project in schedule and learn about project management and scheduling
  Have a working first version integrated into Kactus2
Objectives of the client
  Tool should offer features that make the use of Kactus2 easier (requires user study)
  Tool should be well integrated into Kactus2

## Slide 7: What was done? (1)

## Slide 8: What was done? (2)
Source code parsing and dependency analysis
  C/C++ and VHDL supported
Ability to create manual dependencies
  E.g. between documentation and source files
Dependency visualization in a table-graph format, including
  Changes detection
    File hash calculation
    Dependency difference view
  Filtering
All this represented with a clean, simple UI
  Fully integrated into Kactus2

## Slide 9: Problems Met and Solutions
Not always enough time to work for the project
  Was compensated by team efficiency and careful implementation
    Tasks required less time than expected
    It was possible to reuse more features from Qt than was assumed

## Slide 10: Realized Risks
Sickness
  Caused one week delay which was compensated later on
Development server downtime
  Sourceforge (version control) was temporarily down
  Hostedredmine.com (project management) was down
  No severe effects

## Slide 11: Time Usage
Chart: Monthly Planned vs. Realized Time Usage
| Nov 2012 | Dec 2012 | Jan 2013 | Feb 2013 | Mar 2013 | Apr 2013
Planned | 66 | 66 | 190 | 167 | 110 | 60
Realized | 26.35 | 34.85 | 49.4 | 62.85 | 93.05 | 35

## Slide 12: Time Usage
Chart: Working Hour Distribution
| Reporting | Testing | General Implementation | UI Implementation | Algorithm Implementation | Technical Specification | Functional Specification | T7 | T6 | T5 | T4 | T3 | T2 | T1
Realized | 85.3 | 35 | 19 | 84.25 | 37.75 | 11.35 | 29.35
Planned | 192 | 80 | 30 | 170 | 77 | 50 | 60

## Slide 13: What did we learn?
Scheduling is difficult
  Especially when using libraries you don’t know inside out
  It is better to overestimate than to underestimate
    Although overestimation is not good either
Don’t reinvent the wheel
  30 minutes of research can save hours of work
  Reimplementing an algorithm in a different language is much simpler than figuring it out
  In this project: saved over 80 hours of work
Not all projects are full of problems

## Slide 14: Conclusion
The project was successful
  The first fully functional version of the tool was finished
  All members are now familiar with Qt development
Next steps after the project
  User study to make sure the usability of the tool is good
  Several potential improvements were invented  review and implementation to the next version

## Slide 15: Demo

## Slide 16: Questions?