## Task Summary
ID	Task name	Running weeks	Allocated hours	% of total hours	Related deliverables
T1	Functional specification	46/2012 – 50/2012	60	9,69	Functional specification
T2	Technical specification	50/2012 – 2/2013	50	8,08	Technical specification
T3	Algorithm implementation	2/2013 – 10/2013	77	12,44	Final code
T3.1	Dependency analysis algorithm interface	2/2013 – 3/2013	6	0,97
T3.2	C++ dependency analysis algorithm	2/2013 – 6/2013	20	3,23
T3.3	C++ hash calculation	2/2013 – 3/2013	8	1,29
T3.4	Dependency parser settings	2/2013 – 6/2013	10	1,62
T3.5	VHDL dependency analysis algorithm	6/2013 – 10/2013	25	4,04
T3.6	VHDL hash calculation	6/2013 – 10/2013	8	1,29
T4	UI implemementation	2/2013 – 13/2013	170	27,46	Final code
T4.1	Basic table-style widget	2/2013 – 6/2013	50	8,08
T4.2	Dependency graph visualization	4/2013 – 10/2013	70	11,31
T4.3	Manual dependencies	6/2013 – 10/2013	15	2,42
T4.4	Locking dependencies	6/2013 – 10/2013	10	1,62
T4.5	Filter views	10/2013 – 13-2013	10	1,62
T4.6	Dependency change visualization	10/2013 – 13/2013	15	2,42
T5	General implementation	2/2013 – 13/2013	30	4,85	Final code
T5.1	Folder and file scanning	2/2013 – 4/2013	5	0,81
T5.2	Saving graph data in XML	4/2013 – 7/2013	25	4,04
T6	Testing	2/2013 – 13/2013	80	12,92
T7	Reporting	46/2012 – 16/2012	152	24,56
T7.1	Group meetings	46/2012 – 15/2012	60	9,69	Meeting memos
T7.2	Client meetings	46/2012 – 15/2012	30	4,85	Meeting memos
T7.3	Assistant meetings	48/2012 – 16/2012	10	1,62	Meeting memos
T7.4	Project plan presentation	46/2012 – 48/2012	12	1,94	Project plan presentation
T7.5	Final presentation	14/2012 – 16/2012	15	2,42	Final presentation
T7.6	Final report	14/2012 – 16/2012	25	4,04	Final report
	Total	46/2012 – 15/2012	619

## TaskSchedule
ID	Task name	2012-11 (63)				2012-12 (69)				2013-01 (172)					2013-02 (159)				2013-03 (103)				2013-04 (53)			Hours per task		ID	Task name	2012-11 (63)				2012-12 (69)				Hours per task 2012			ID	Task name	2013-01 (182)					2013-02 (159)				2013-03 (103)				2013-04 (53)			Hours per task 2013					Running weeks	Allocated hours	% of total hours	Related deliverables
		45	46	47	48	49	50	51	52	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16					45	46	47	48	49	50	51	52					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16
T1	Functional specification		12	12	12	12	12					60		T1	Functional specification		12	12	12	12	12			60			T1	Functional specification					0					46/2012 – 50/2012	60	12	Functional specification
T2	Technical specification					10	10	10	10	10					50		T2	Technical specification					10	10	0	20			T2	Technical specification	18	12					30					50/2012 – 2/2013	50	10	Technical specification
T3.1	Dependency analysis algorithm interface					3	3					6		T3.1	Dependency analysis algorithm interface					0			T3.1	Dependency analysis algorithm interface		3	3					6					2/2013 – 3/2013	6	#REF!
T3.2	C++ dependency analysis algorithm					4	4	4	4	4					20		T3.2	C++ dependency analysis algorithm					0			T3.2	C++ dependency analysis algorithm		4	4	4	4	4					20					2/2013 – 6/2013	20	#REF!
T3.3	C++ hash calculation					4	4					8		T3.3	C++ hash calculation					0			T3.3	C++ hash calculation		4	4					8					2/2013 – 3/2013	8	#REF!
T3.4	Dependency parser settings					2	2	2	2	2					10		T3.4	Dependency parser settings					0			T3.4	Dependency parser settings		2	2	2	2	2					10					2/2013 – 6/2013	10	#REF!
T3.5	VHDL dependency analysis algorithm					5	5	5	5	5					25		T3.5	VHDL dependency analysis algorithm					0			T3.5	VHDL dependency analysis algorithm					5	5	5	5	5					25					6/2013 – 10/2013	25	#REF!
T3.6	VHDL hash calculation					1	1	2	2	2					8		T3.6	VHDL hash calculation					0			T3.6	VHDL hash calculation					1	1	2	2	2					8					6/2013 – 10/2013	8	#REF!
T4.1	Basic table-style widget					10	10	10	10	10					50		T4.1	Basic table-style widget					0			T4.1	Basic table-style widget		10	10	10	10	10					50					2/2013 – 6/2013	50	#REF!
T4.2	Dependency graph visualization					10	10	10	10	10	10	10					70		T4.2	Dependency graph visualization					0			T4.2	Dependency graph visualization				10	10	10	10	10	10	10					70					4/2013 – 10/2013	70	11,67
T4.3	Manual dependencies					3	3	3	3	3					15		T4.3	Manual dependencies					0			T4.3	Manual dependencies					3	3	3	3	3					15					6/2013 – 10/2013	15	#REF!
T4.4	Locking dependencies					2	2	2	2	2					10		T4.4	Locking dependencies					0			T4.4	Locking dependencies					2	2	2	2	2					10					6/2013 – 10/2013	10	#REF!
T4.5	Filter views					3	2	2	3				10		T4.5	Filter views					0			T4.5	Filter views					3	2	2	3				10					10/2013 – 13-2013	10	#REF!
T4.6	Dependency change visualization					3	4	4	4				15		T4.6	Dependency change visualization					0			T4.6	Dependency change visualization					3	4	4	4				15					10/2013 – 13/2013	15	#REF!
T5.1	Folder and file scanning					2	1	2					5		T5.1	Folder and file scanning					0			T5.1	Folder and file scanning		2	1	2					5					2/2013 – 4/2013	5	#REF!
T5.2	Saving graph data in XML					6	6	6	7					25		T5.2	Saving graph data in XML					0			T5.2	Saving graph data in XML				6	6	6	7					25					4/2013 – 7/2013	25	#REF!
T6	Testing					4	4	4	4	6	6	6	8	8	10	10	10				80		T6	Testing					0			T6	Testing		4	4	4	4	6	6	6	8	8	10	10	10				80					2/2013 – 13/2013	80	#REF!
T7.1	Group meetings		3	3	3	3	3	3			3	3	3	3	3	3	3	3		60		T7.1	Group meetings		3	3	3	3	3	3		18			T7.1	Group meetings		3	3	3	3	3	3	3	3		42					46/2012 – 15/2012	60	#REF!	Meeting memos
T7.2	Client meetings			3		3		3				3		3		3		3		3		3		3		30		T7.2	Client meetings			3		3		3		9			T7.2	Client meetings			3		3		3		3		3		3		3		21					46/2012 – 15/2012	30	#REF!	Meeting memos
T7.3	Assistant meetings				3					3					4			10		T7.3	Assistant meetings				3					3			T7.3	Assistant meetings				3					4			7					48/2012 – 16/2012	10	#REF!	Meeting memos
T7.4	Project plan presentation		2	4	6					12		T7.4	Project plan presentation		2	4	6					12			T7.4	Project plan presentation					0					46/2012 – 48/2012	12	#REF!	Project plan presentation
T7.5	Final presentation					3	6	6	15		T7.5	Final presentation					0			T7.5	Final presentation					3	6	6	15					14/2012 – 16/2012	15	#REF!	Final presentation
T7.6	Final report					5	10	10	25		T7.6	Final report					0			T7.6	Final report					5	10	10	25					14/2012 – 16/2012	25	#REF!	Final report
	Hours per week	0	17	22	24	18	25	16	10	10	42	34	44	42	52	40	31	36	39	22	19	23	15	22	16	619			Hours per week	0	17	22	24	18	25	16	0	122				Hours per week	18	44	34	44	42	52	40	31	36	39	22	19	23	15	22	16	497					46/2012 – 15/2012	#REF!
	Deliverables					D1				D2					C1	FR				Deliverables					D1					Deliverables		D2					C1	FR
	Meetings				A1					A2					A3					Meetings				A1					Meetings				A2					A3

				LEGEND
				ID	Meetings/Reviews	Attendance	Notes
				A1	Milestone meeting 1	Assistant, group
				A2	Milestone meeting 2	Assistant, group
				A3	Milestone meeting 3	Assistant, group
				ID	Deliverable	Delivery recipients	Notes
				D1	Functional specification	Client, assistant
				D2	Technical specification	Client, assistant
				C1	Qt implementation of the tool	Client
				FR	Final report	Client, assistant
				M1	Monthly status reports 2012 (Nov, Dec)	Assistant
				M2
				M3	Monthly status reports 2013 (Jan, Feb, Mar)	Assistant
				M4
				M5
				P1	Project plan presentation	Seminar
				P2	Final report presentation and live demonstration	Seminar

## Task Costs
Project costs (personal example)
					ID	Task name	Allocated hours	Task cost
type of expense:					T1	Functional specification	60	840 €
Personnel costs					T2	Technical specification	50	700 €
Working hours	650			Salary after taxes?		T3	Algorithm implementation	77	1 078 €
Salary per hour	14 €			8 €		T3.1	Dependency analysis algorithm interface	6	84 €
Salaries for project	9 100 €			5 460 €		T3.2	C++ dependency analysis algorithm	20	280 €
Indirect employee costs	3 640 €	40 %		1 820 €		T3.3	C++ hash calculation	8	112 €
Personnel costs total	12 754 €					T3.4	Dependency parser settings	10	140 €
					T3.5	VHDL dependency analysis algorithm	25	350 €
Travel	50 €	VAT excluded				T3.6	VHDL hash calculation	8	112 €
Equipment	0 €					T4	UI implemementation	170	2 380 €
Licences	0 €					T4.1	Basic table-style widget	50	700 €
Consumables and material	50 €					T4.2	Dependency graph visualization	70	980 €
Subcontracting	0 €					T4.3	Manual dependencies	15	210 €
Other costs	0 €					T4.4	Locking dependencies	10	140 €
Other costs total	100 €					T4.5	Filter views	10	140 €
					T4.6	Dependency change visualization	15	210 €
Total project expences	12 854 €					T5	General implementation	30	420 €
Profit	0 €	0 %				T5.1	Folder and file scanning	5	70 €
Price of the project	12 854 €					T5.2	Saving graph data in XML	25	350 €
Price of the project (vat 23% inc)	15 810 €					T6	Testing	80	1 120 €
					T7	Reporting	152	2 128 €
					T7.1	Group meetings	60	840 €
VAT is different for different cost types (travel, equipment)					T7.2	Client meetings	30	420 €
					T7.3	Assistant meetings	10	140 €
					T7.4	Project plan presentation	12	168 €
					T7.5	Final presentation	15	210 €
					T7.6	Final report	25	350 €
					Total	619	8 666 €